Homework 2 – Estimating	/ 50

Instructions

- Submit as one Word document via email

- Document Name shall be:  Homework3-<LastName,FirstName>

  - Example    	Homework3-Snerfle,Burf

- Email Subject Line shall be: CSCI3350-<Your Section Number>:Homework3

  - Example	CSCI3350-001:Homework3

- Due: 26 Sept, via email prior to noon

Questions

- Clearly distinguish between accuracy and precision with respect to an estimation model.  (2 pts)

- You are a software engineer at Burf’s Software Shysters.  Your manager announced that your next product would consist of 19 files, of which 3 are temporary files and 6 are transaction files.  There are 19 input screens, 21 output screens, 43 error dialog screens, and 87 processes.
Using the FFP metric, determine the product size.    (2 pts)

- At Burf’s Software Shysters, the constant d has a value of $719.  What cost estimate does the FFP metric predict?    (2 pts)

- The product of problem 2 and 3 was recently completed with a total cost of $122,800.  What does this tell you about the productivity of your development team, as compared to Burf’s Software Shysters as a whole?   (2 pts)

- A target product has 9 simple inputs, 4 average inputs, and 5 complex inputs.  There are 46 average outputs, 11 simple inquiries, 7 average master files, 6 simple interfaces, 8 average interfaces and 13 complex interfaces.  Determine the unadjusted function points (UFP).   (2 pts)

- If the total degree of influence for the product in problem 9 is 41, determine the number of function points.   (2 pts)

- The analysts in your group have estimated another project to have 1165 function points. Using the heuristics from Caper Jones, estimate the

  - The number of source code statements for a procedural implementation language,

  - The number of test cases required,

  - Total lifecycle errors,

  - The development schedule ,

  - The number of development personnel needed,

  - The level of effort,

  - The number of maintenance programmers needed, and

  - The number of years the product will be used

- Suppose that you have estimated that an application has a total of 44 classes.  You know that your organization has a productivity constant of 18.3.  Using the Lorenz and Kidd model estimate the number of man-days required to complete the project. (2 pts)

- Burf’s Software Shysters has compiled the following data from their past contracts.

| Size (KLOC) | Effort (man-months) |
| --- | --- |
| 104.09 | 80.19 |
| 9.53 | 5.99 |
| 89.47 | 110.34 |
| 27.77 | 21.72 |
| 8.49 | 5.94 |
| 38.22 | 37.08 |
| 91.80 | 86.43 |
| 42.29 | 15.45 |
| 64.77 | 58.67 |
| 65.75 | 44.12 |
| 86.46 | 92.65 |
| 91.20 | 60.50 |
| 44.95 | 29.92 |
| 40.31 | 49.56 |
| 97.29 | 105.21 |
| 30.33 | 37.68 |
| 25.92 | 23.84 |

Assuming a simple static effort as a function of size model of the form

Using the technique demonstrated in class,

  - Determine the values for A and B , analytically.   (4 pts)

  - Create an Excel Chart showing the data with an overlay of the fit.   (4 pts)

- You have been asked to prepare a bid for an upcoming project based upon the following labor categories for your company:

|  | Level | Hourly Rate |
| --- | --- | --- |
| Technical Manager | 3 | $76.92 |
|  | 2 | 57.69 |
|  | 1 | 45.67 |
| Software Engineer | 4 | 86.54 |
|  | 3 | 72.12 |
|  | 2 | 57.69 |
|  | 1 | 48.08 |
| Programmer | 4 | 62.5 |
|  | 3 | 48.08 |
|  | 2 | 38.08 |
|  | 1 | 28.85 |
| Support | 2 | 19.23 |
|  | 1 | 13.46 |

  - Management has provided the following estimates for personnel categories

|  | Level | Billable Man Years |
| --- | --- | --- |
| Technical Manager | 2 | 2 |
| Software Engineer | 4 | 2 |
|  | 3 | 4.1 |
|  | 2 | 5.6 |
|  | 1 | 6.3 |
| Programmer | 4 | 4.2 |
|  | 3 | 3.7 |
|  | 2 | 12.1 |
|  | 1 | 6.2 |
| Support | 2 | 4.4 |
|  | 1 | 4.5 |

Given that a Man Year is 2080 hours and employees receive 3 weeks paid vacation per year, 10 paid holidays per year, and 12 day of sick leave per year, calculate the Total Direct Labor Dollars.  (2 pt.)

  - The Overhead Rate for your company is 1.09.  Calculate the Overhead Costs.   (2 pt.)

  - Management estimates that $8,500.00 will be spent for Document preparation, $51,965.00 for consultants, and $236,899 for the purchase of hardware.  Calculate the total of  Other Direct Costs.   (2 pt.)

  - What is the Total Project Cost?   (2 pt.)

  - Given a fee rate of 6.6%, what is the Total Fee?   (2 pt.)

  - What is the Total Project Price?    (2 pt.)