## Slide 1: Lecture 4 Project Estimation
CSCI – 3350 Software Engineering II
Fall 2014
Bill Pine

## Slide 2: Planning Prerequisites
The planning process requires the following inputs:
  Required human effort (man-months)
  Project duration (months)
  Project costs ($)
We would like our estimates to be perfectly precise and accurate
  But this requirement is impossible until the project is over
    Why? (more later)

## Slide 3: Importance of Estimates
In the early days of computing,
  Software costs were a small part of the total system cost
    Even large errors (order of magnitude) = little impact on the total system cost
  Today, software costs are the largest component of total system cost
    Large errors in estimating cost equate to
      The difference between profit and loss or
      Survival and demise

## Slide 4: Reasons for Inaccuracy in Estimates
Too many uncertainties in the variables that determine the cost
In the following categories
  Human
    The developers and their skills are not perfectly known
  Technical
    May need to use new or unfamiliar technology
  Environmental
    May need to run on unfamiliar computer or operating systems
  Political
    Internal company or client politics

## Slide 5: Estimation Techniques
Five main categories of techniques
  Algorithmic models
  Expert judgment
  Estimation by analogy
  Pricing to win
  Parkinson pricing

## Slide 6: Algorithmic Models
A formula (or set of formulae) is evaluated to provide an estimate
Size or functionality metrics are the independent variables
Constants in the formula are based upon historic cost data

## Slide 7: Expert Judgment
Several experts in the application domain independently prepare estimates
Estimates are compared (together with the rationale for the estimate)
Differences are resolved by discussion
It is not
  Estimation by committee
  An averaging of the independent estimates

## Slide 8: Estimation by Analogy
Cost of a new project is estimated by analogy to similar systems previously developed
  Identify differences and estimate cost of these differences
How to handle no previously developed similar systems?
What about changes in development environment?
  How to handle employee turnover?
  How to handle new language, case tools, …

## Slide 9: Pricing to Win
The cost is what you believe the customer is willing to spend
What circumstances would lead you to price a project this way?

## Slide 10: Parkinson Pricing
Parkinson’s Law
  Parkinson’s Law – The work expands to fill the time available
Cost is determined by available resources rather than by objective analysis
Example
  If the software is needed in 1 year and you have 5 developers available to work on the project, the effort is 60 man-months

## Slide 11: Importance of Deviation
It is important to identify changes from previous projects, especially when employing
  Expert Judgment or
  Estimation by Analogy
Examples of change affecting estimates
  Object-oriented versus structured techniques
  Client-server systems versus stand-alone applications
  COTS components versus developed components
  Reuse versus all new development
  CASE tools / code generators versus unsupported development

## Slide 12: Importance of Deviation (cont)
Failure to identify change and account for its influence
  Distorts the estimate
    Perhaps to the point that the estimate is of little value

## Slide 13: Algorithmic Cost Modeling
The most systematic approach to cost modeling
  The most precise method, but
  Don’t confuse with the most accurate
A formula or set of formulae is used to predict cost based on project size, and sometimes other project factors
Most algorithmic cost models have an exponential component
  Realizing that cost does not scale linearly with size

## Slide 14: Algorithmic Modeling (cont)
The simplest model is a static single-variable model
Where
  A is a constant factor
    Factor incorporating process, product and development characteristics
  Size code size or a function oriented value
  B A constant typically in the range of 1 to 1.5

## Slide 15: Size Metrics
Two common categories of size metrics
  Lines of code
  Function oriented metrics
While lines of code (LOC) not the only size metric
  LOC is the most commonly used measure of size

## Slide 16: LOC Metric
There are two different ways of implementing LOC
  Lines of Code (LOC or KLOC)
    Count all lines
  Thousand of delivered source instructions (KDSI)
    Count of the physical source statements, includes:
      Format statements
      Data declarations
    Excludes
      Comments
      Unmodified utilities

## Slide 17: Class Exercise
List the problems associated with lines of code as a metric
Time: 10 minutes

## Slide 18: Function Oriented Metrics
Based upon a higher level of abstraction
  Identify and score high level functionality
We will example two metrics
  FFP
    Based on three characteristics:
      Files, flows and processes
  Function points
    Based on five characteristics
      Input items, Output items, Inquiries, Master files, Interface

## Slide 19: FFP
Proposed by van der Poel and Schach
  Medium Size Projects ( 1- 10 man years)
  Identify and score 3 basic structural elements
    Files, Flows, and Processes
Structural elements
  Files
    Permanent files only
      Do not count temporary or transaction files

## Slide 20: FFP (cont)
  Flows
    Interfaces between the product and the environment
      Input / Output Screens
      Reports
  Processes
    Functionally coherent manipulations of data
      Sorting
      Validating
      Transforming

## Slide 21: FFP (cont)
Size
  The size is the sum of the Files, Flows and Processes
Cost
  The product of Size and a constant d
    Constant varies from organization to organization
    Based on historic cost and size data

## Slide 22: FFP (cont)
Note:
  This metric is based upon the functionality of the application
    High level property of the system
    Can be more accurate earlier in the life-cycle than LOC metrics

## Slide 23: Class Exercise
An application maintains 8 files: a sorted master data file, 3 index files, 1 transaction file and 3 temporary files. It has 3 data input screens, 3 display screens, generates 4 printed reports, and 6 error message boxes. The processing includes sorting the master file, updating transactions, calculating report data from master file data. Assume a value of 800 for d .
Determine the Size and Cost using FFP.
Time = 5 min

## Slide 24: FFP Summary
Advantages
  A simple algorithmic model
    Based on easy-to-count characteristics of a high level design
Disadvantages
  All items are equally weighted
  Requires historic data based upon a particular organization
  Has not been extended to correctly count databases
  Something unsettling about adding unlike quantities

## Slide 25: Function Points
A similar approach taken by Albrecht
Based on 5 functionality characteristics
  Input items, output items, inquiries, master files, and interfaces
First calculate the number of unadjusted function points

## Slide 26: Function Points (cont)
The constants are determined from the following table

## Slide 27: Function Points (cont)
The next step is to calculate a technical complexity factor
Each of 14 technical factors is assigned a value from 0 to 5
  0 - Not present or no influence
  5 - Strong influence throughout
The degree of influence DI obtained by summing the above values

## Slide 28: Function Points (cont)
The 14 technical factors are
Data communication Online updating
Distributed data processing Complex computations
Performance criteria Reusability
Heavily utilized hardware Ease of installation
Online data entry Ease of operation
End-user efficiency Maintainability
Transaction Rate Multiple Sites

## Slide 29: Function Points (cont)
Calculate the technical complexity factor TCF
  TCF values are in the range of 0.65 to 1.35
Finally the number of function points FP is calculated from

## Slide 30: Function Point Calculations
You may find the following template useful
  What might be an even better alternative to the template?

## Slide 31: Class Exercise
An application has 5 simple inputs, 4 complex inputs, 30 average outputs, 5 simple queries, 10 average master files and 8 complex interfaces. The degree of influence is 50. Calculate the number of unadjusted function points and the number of function points.
Time = 10 minutes

## Slide 32: Simple Object-Oriented Estimation
Simple four step model developed by Lorenz and Kidd
The number of estimated classes serves as the size parameter

## Slide 33: The Four Steps
Determine the number of problem domain classes in the application
Determine the interface and the associated weight
Calculate the number of total classes by multiplying the number of problem domain classes by the interface weight and add it to the number of problem domain classes
Calculate the number of man-days by multiplying the total number of classes by a productivity constant in the range of 15 - 20

## Slide 34: Interface Weights
Interface Type | Weight
No user interface | 2.0
Simple text-based interface | 2.25
Graphical user interface | 2.5
Complex graphical user interface | 3.0

## Slide 35: Class Exercise
An object-oriented application has an estimated 50 problem domain cases and a graphical user interface. Assuming a productivity constant of 18, calculate the number of man-days that will needed to develop the application.
Time = 10 minutes

## Slide 36: COCOMO
COCOMO is a static single variable model
COCOMO is an acronym for Constructive Cost Model that was developed by Barry Boehm
COCOMO is actually a hierarchy of models of the following form
  Basic COCOMO – estimates software development effort and cost as a function of program size in lines of code
  Intermediate COCOMO - estimates software development and cost as a function of program size in lines of code and a set of “cost drivers”

## Slide 37: COCOMO (cont)
  Cost drivers include subjective assessments of attributes in the general areas of
    Product
    Hardware
    Personnel
    Project
  Advanced COCOMO – incorporates the characteristics of intermediate COCOMO with an assessment of the cost driver impact on each phase of the software development cycle

## Slide 38: COCOMO (cont)
We will confine our examination to the intermediate model
The intermediate model calibrated on
  40 software development projects
Further work revealed certain difficulty factors that dramatically influenced the effort estimates and schedule

## Slide 39: COCOMO (cont)
The level of difficulty was broken into three modes
  Organic Mode
    Constraints on development are mild
    Many similar projects previously developed by the organization
  Semi-detached Mode
    More constraints on development, but some flexibility remains
    Few similar projects previously developed by the organization
  Embedded Mode
    Very tight constraints
    No similar projects previously developed

## Slide 40: Intermediate COCOMO Calculations
Intermediate COCOMO calculations proceed by
  First, determine the mode (organic, semi-detached, embedded)
  This determines the constants A - D

## Slide 41: Intermediate COCOMO (cont)
  Second, using the appropriate constants from the previous table, calculate the nominal effort and schedule from
  Third, calculate a difficulty multiplier that depends upon the previous mention categories
    Product
    Hardware
    Personnel
    Project

## Slide 42: Intermediate COCOMO (cont)
  Fourth, the adjusted effort MM is the nominal effort MMnominal multiplied by the difficulty multiplier
  Fifth, the project duration is calculated from

## Slide 43: Intermediate COCOMO (cont)
With regard to the accuracy of COCOMO, heed the words of Barry Boehm
  “Today, a software cost estimation model is doing well if it can estimate software development costs within 20% of actual costs, 70% of the time, and on its own turf (that is within the class of projects to which it has been calibrated) ... This is not as precise as we might like, but it is accurate enough to provide a good deal of help in software engineering economic analysis and decision making [sic].”

## Slide 44: COCOMO II
COCOMO II was developed to address several issues that did not exist when the original COCOMO was developed
  The waterfall model was the software lifecycle development model
  Most software ran on mainframes
  Client-server and object oriented technologies were unknown, or at least were not widely used
  Simple reuse in effect – no inheritance, etc

## Slide 45: COCOMO II (cont)
Major differences
  COCOMO was based upon lines of codes estimate
    COCOMO II allows the use of other metrics, i.e. function points
  COCOMO had a constant exponent, depending upon which of three modes is selected
    COCOMO II allows the exponent to continuously vary between 1.01 and 1.26
  COCOMO assumes that savings due to reuse are directly proportional to the amount of reuse
    COCOMO II uses a non linear model – even a small amount of reuse may incur a huge effort in understanding the code

## Slide 46: COCOMO II (cont)
  COCOMO II modified the difficulty factors
  COCOMO II was calibrated with 83 projects

## Slide 47: Additional Considerations
Consider adding the following multiplier to all estimates