## Slide 1: Lecture 2 Project Planning
CSCI – 3350 Software Engineering II
Fall 2014
Bill Pine

## Slide 2: Lecture Overview
CSCI 3350
Lecture 2 - 2
The Project Plan
Work Breakdown Structure
Introduction to Schedules
Project Vision Statements

## Slide 3: Introduction
CSCI 3350
Lecture 2 - 3
Poor project management is one of the chief causes of project failure
What is project failure?
A major component of project management is planning
Good planning will not guarantee project success, but
  Poor planning (or no planning) begets project failure

## Slide 4: The Software Management Plan
CSCI 3350
Lecture 2 - 4
A sound plan is the project manager’s most important tool for project success
Key elements of a Software Project Management Plan
  Overview
    One-page description of project functionality, target platform, customer(s) and schedule

## Slide 5: The Management Plan (cont)
CSCI 3350
Lecture 2 - 5
  High Level Functionality
    Two to four page description of the top-level functionality of the product
    Maintained to be consistent with the TLR and SRS
  Project Staffing
    Description of the specific information on
      Software engineering roles and
      Personnel assigned to those roles
  Software Process
    Description of the software development process model chosen for the project

## Slide 6: The Management Plan (cont)
CSCI 3350
Lecture 2 - 6
  Schedule
    Detailed description of the project activities, milestones and events
    Together with the associated due dates / durations
    Include a discussion of assumptions that have an impact on the schedule
  Metrics
    Specific list of the quantities that will be measured
    Together with the role that will take and record the measurements
    Also include a description of the metrics’ analysis and reporting

## Slide 7: The Management Plan (cont)
CSCI 3350
Lecture 2 - 7
  Project Risks
    List of identified project risks
    Presented in the “top-ten” format
    “Top-ten” list contain five columns:
      This Week’s Position
      Weeks on List
      Risk
      Last Week’s Position
      Resolution Progress
    Include a one-paragraph description of each risk, in order of decreasing risk

## Slide 8: The Management Plan (cont)
CSCI 3350
Lecture 2 - 8
  Deliverables
    List of the deliverables for the project
  References
    List of all documents referenced elsewhere in the SMP
      Title
      Author
      Report number
      Date
      Publisher

## Slide 9: The Management Plan (cont)
CSCI 3350
Lecture 2 - 9
No surprise, there is an IEEE Standard for the Software Project Management Plan (SPMP)
  IEEE – 1058 Software Project Management Plan Standard

## Slide 10: Work Breakdown Structure (WBS)
CSCI 3350
Lecture 2 - 10
The WBS is the foundation for project planning and control
Initially developed by the US defense community
  The WBS is formalized in a Mil Standard – 881B
What is a WBS?
  A hierarchical framework that supports the decomposition of a project into progressively smaller pieces
  The topmost level is a single entry the project name
    e.g. “ATM Machine”
  The lowest level must represent a single “chunk” of work that can be scheduled and budgeted
    It is described by a verb or verb phrase
    Does not necessarily equate to the smallest piece in the design

## Slide 11: WBS (cont)
CSCI 3350
Lecture 2 - 11
  Intermediate levels are described by noun phrases
  How small is small enough?
    Real World Heuristic:
    An element at the lowest level will need 1 to 8 man-weeks to complete
  For our one semester project, the upper limit of 8 weeks is too great
    One week or less as a maximum

## Slide 12: How To Create a WBS
CSCI 3350
Lecture 2 - 12
Two general approaches
  Depending upon the contents of the first level
    Deliverable-based
    Workflow-based
Prefer Deliverable-based over Workflow-based
  You want to make sure that the project focuses on deliverables, and
  Ensure all deliverables are met

## Slide 13: Create a Deliverables Based WBS
CSCI 3350
Lecture 2 - 13
Begin with a list of deliverables
The deliverables become the entries for Level 2 of your WBS
  Remember these are nouns / noun phrases
    System prototype
    System test plan
Next decompose (breakdown) each of these into their component parts
  Each of the pieces must be unique
  An obvious part of the entry above

## Slide 14: Create WBS (cont)
CSCI 3350
Lecture 2 - 14
Continue until you reach the “right” level of detail
  Should be a small enough piece that you know
    What needs to be done and the approximate effort
  Be sure to add a verb to the beginning of the name
    Develop Algorithm For Tri-Phase Snerfle Sort
    Write Section 3 of The SMP
  Avoid weak verbs such as do, perform

## Slide 15: Create WBS (cont)
CSCI 3350
Lecture 2 - 15
Review for completeness of deliverables
  The above decomposition may (likely will) result in further deliverables
    Design documentation
    Requirements documentation
    Testing documentation
  Decompose each of the newly added deliverables to the same level of detail
  Review the structure to see if it is out of balance
    Balance = branches are of approximately equal length
    Consider further decomposition or combination to produce a better balance

## Slide 16: WBS Validation
CSCI 3350
Lecture 2 - 16
When you believe that your WBS is complete, validate with a bottom up approach
  For each WBS element that decomposes into activities (name is a verb phrase)
    Ask the question: “If I had all the deliverables from all the activities, would this WBS element deliverable be complete?”
    If yes, move on the next element
    If no, add the missing activities
  When the lowest level WBS elements are complete, move up 1 level and repeat

## Slide 17: WBS Validation (cont)
CSCI 3350
Lecture 2 - 17
This validation phase is very important. The chief cause of project overruns is unplanned work.
  The money and time to carry out “surprise” work, must come from somewhere
  Unlike Uncle Sugar, we can’t just “crank up the presses”
When you have completed the bottom-up validation, ask the following question
  If I had all the deliverables, would I achieve the planned objectives for this project?
  If not, make another pass through the WBS, adding deliverables and activities as necessary

## Slide 18: Observations on the WBS
CSCI 3350
Lecture 2 - 18
The driver for the WBS is the set of project deliverables
  Focus on the deliverables
    Then the activities that will produce them
  While the activities are the heart of a project schedule
    Ensure the project activities are directed toward project deliverables

## Slide 19: Observations (cont)
CSCI 3350
Lecture 2 - 19
It is easy to get involved with the WBS, and produce a very detailed WBS, with many levels
How many levels should there be?
  Unless the project is very large,
    5 is a good rule of thumb for the maximum levels
    A small to medium project may need only 3 levels
  Any more levels, and the details become too much to manage

## Slide 20: Observations (cont)
CSCI 3350
Lecture 2 - 20
Too many levels?
  You may have defined work in too great a detail (activities too small)
  A deliverable may be too broadly defined. Break it up and spread it horizontally rather than vertically

## Slide 21: Amount of Detail
CSCI 3350
Lecture 2 - 21
A common mistake is to include too much detail, too many tasks
  It is all too easy to continue to decompose until you end up with a list of 1 hour tasks
What forces make this happen?
  It makes the project manager feel that he is in control.
    He has this “master list” of 37,481 items
    As each one is completed, he checks it off
    When the last item is checked, the project is completed (Yeah, right)

## Slide 22: Amount of Detail (cont)
CSCI 3350
Lecture 2 - 22
  Upper management interprets this as a sign that the project is under control
  The customer is led to believe that the project manager has thought of everything
    He hasn’t, no project manager can

## Slide 23: Amount of Detail (cont)
CSCI 3350
Lecture 2 - 23
Bad project manager, bad, bad
  It encourages the project manager to micro-manage
    Kills initiative of the team
    Encourages reliance upon the manager rather than team members
  Managers are more effective when they encourage people to reach objectives, not completing a list of tasks
  The huge list is too hard to maintain
    You do remember that we need to manage change?
    When the crunch comes, the list will likely be abandoned because there isn’t enough time to do it

## Slide 24: Reading Assignment
Before next time, read the paper at :
Work Breakdown Structure
Be prepared to discuss the paper
CSCI 3350
Lecture 2 - 24

## Slide 25: A WBS Methodology
CSCI 3350
Lecture 2 - 25
A very effective method for producing the first draft of the WBS is to use blank sheets of paper, Magic Markers, tape, and a blank wall. 8 ½ X 11 size seems to work well
For small groups, Post-It sheets on a table top can work
  Write the names of the major deliverables on the sheets, 1 per sheet
If the deliverable is large, break it down, putting each part on a separate sheet, but don’t get carried away with too much detail. Only decompose to a level, where you understand
  The activity necessary to produce it
  How to estimate the effort

## Slide 26: A WBS Methodology (cont)
CSCI 3350
Lecture 2 - 26
For each deliverable, describe the activities necessary to compete it
  One activity per sheet
    Check each activity to make sure that it meets the size criteria
    1 to 8 man-weeks to complete
  If it does not meet the criteria
    Decompose or combine as necessary

## Slide 27: A WBS Methodology (cont)
CSCI 3350
Lecture 2 - 27
Advantages
  Easy to visualize the WBS
  Your entire team can participate
  Easy to rearrange items
  Easy to combine or decompose items

## Slide 28: Class Exercise
CSCI 3350
Lecture 2 - 28
For some time now, your spouse has wanted a garden shed. Because you can never seem to find the time to build it, you decided to hire a contractor. Prefab units do not appeal to your spouse. You get bids from several local contractors and the cost is staggering. You are bemoaning this sorry state of affairs to your neighbor, Wilson, when he suggests that you hire a group of neighborhood teenagers on a CPFF (Cost-Plus-Fixed-Fee) basis. You talk to several of the teenagers, and they are interested.

## Slide 29: Class Exercise (cont)
CSCI 3350
Lecture 2 - 29
Two problems arise: you want to ensure that you get a quality product, and the teenagers are unable to finance the total cost of materials. Fortunately, the uncle of one of the teenagers is the owner of Bobarino’s Bodacious Building Bazaar and he is willing to extend limited credit to the team. You decide to have the team create a work breakdown structure (WBS) to ensure a quality product. Progress payments will be based upon the WBS.
The purpose of this exercise is to produce a WBS that has a generous number of deliverable that you can use as a measure of when and how much to pay.

## Slide 30: Project Schedule Inputs
CSCI 3350
Lecture 2 - 30
Project planning determines a project schedule based upon
  Project constraints
    Start date and Duration
    Staff
    Budget
  Project parameters
    Structure
    Size
    Functionality
  Project milestones and deliverables

## Slide 31: Milestones
CSCI 3350
Lecture 2 - 31
Major events that occur during the course of the project
  Characteristics
    Point in time – no duration
    Represent major achievements during development
    Of major interest to all stakeholders
    Named in the past tense to indicate that it is not an ongoing activity
      Acceptance Tests Started
      Acceptance Tests Completed

## Slide 32: Project Vision
CSCI 3350
Lecture 2 - 32
During the initial planning, the development team needs to produce a vision statement
The purpose of the vision statement
  Keep the team efforts directed by providing a common set of objectives
A study of 75 teams found that
  In every instance where the team was successful, the team had a clear understanding of its objectives

## Slide 33: Characteristics of a Vision Statement
CSCI 3350
Lecture 2 - 33
Should be focused
  Keeps the team directed
  Avoids expending effort on interesting, but non-productive, bells and whistles
  Hard to develop a team spirit if the team members don’t share a common vision
Should be elevating
  Teams need a challenge
  No one can get “pumped” by a weak vision statement
  Compare
    We’re number two and that’s okay with us
    We’re number two and we try harder

## Slide 34: Vision Statement (cont)
CSCI 3350
Lecture 2 - 34
  Must be achievable
    Setting impossibly high goals can be effective for some professions
      Sales
      Marketing
    For computer professionals impossibly high goals tends not to work well
      Morale drops
      Motivation drops
      Team member look for another project

## Slide 35: Microsoft Example
CSCI 3350
Lecture 2 - 35
Steve McConnell gives the following example
Initial Vision Statement for MS Word
  Create the world’s best word processor
  Provides no guidance regarding which features should be included and which features should be excluded
  Obviously the world’s best word processor will have all features
  Crippled the Word Version 1.0 team
    4 years late in delivery
McConnell suggest a more useful vision statement
  Create the world’s easiest-to-use word processor
  Just as elevating
  But provides a basis for excluding features

## Slide 36: Vision Statement Template
CSCI 3350
Lecture 2 - 36
A template based on the following keywords yields a starting point for a complete, vision statement (Weigers 2003, p85)
  For [target customer]
  Who [statement of need or opportunity]
  The [product name]
  Is [a product category]
  That [key benefit, compelling reason to buy]
  Unlike [primary competition or current system]
  Our Product [statement of advantages of new product]

## Slide 37: Vision Statement Example
CSCI 3350
Lecture 2 - 37
Case Study Vision Statement
  Household Employee Tax Calculator
For homeowner (with a small number of domestic employees), who needs to comply with federal reporting requirements, the HETCal is a payroll management system that will provide employers a convenient means to manage all data associated with paying employees. The system will store the employee tax data and pay period hours worked, calculate the pay period wages and taxes, create quarterly tax withholding report, and year-end tax reports. Unlike payroll systems designed for large companies, our product is easy to setup and use, prints employee paychecks upon demand, and generates all necessary information for your current accountant. This ease of use facilitates compliance with federal employer reporting requirements.

## Slide 38: Project Vision Statement Polishing
A vision statement created according to the template is likely to be convoluted
  Edit and revise the vision statement to improve the readability
Why bother with the template?

## Slide 39: Class Exercise
CSCI 3350
Lecture 2 - 39
Develop a vision statement for the garden shed

## Slide 40: Key Concepts Summary
CSCI 3350
Lecture 2 - 40
Poor project management is a major contributor to project failure
A sound project plan is the project manager’s most useful and powerful tool
The IEEE provides a standard for the Software Project Management Plan

## Slide 41: Key Concepts Summary (Cont)
CSCI 3350
Lecture 2 - 41
A properly executed WBS provides all necessary inputs for creating a project schedule
A good project vision statement helps direct the development team’s efforts toward the successful completion of the project

## Slide 42: Final Thought
CSCI 3350
Lecture 2 - 42
“Plans are nothing; planning is everything.”
-Dwight D. Eisenhower

## Slide 43: References
CSCI 3350
Lecture 2 - 43
Weigers, Karl E. 2003. Software Requirements. Redmond, WA: Microsoft Press.