## Slide 1: Lecture 3 Scheduling
CSCI – 3350 Software Engineering II
Fall 2014
Bill Pine

## Slide 2: Motivation for Scheduling
A schedule is The tool for
  Determining if the project is on time
  Reallocating if the project is not on time
  Ensuring resources are available when needed
  Ensuring personnel can be efficiently utilized

## Slide 3: Developing a Schedule
The starting point for the project schedule
  The work breakdown structure (WBS)
If WBS is properly executed
  Detailed enough to provide reasonably accurate estimates of task effort
  Contains all deliverables, and all tasks necessary to produce the deliverables
We’ll begin by examining a Gantt chart

## Slide 4: Creating a Gantt Chart
Revisit the WBS
  Review the effort (man-months)
Steps to a Gantt chart
  Assign personnel to each task
  Assign a start time to each task and event time to each milestone
  Draw a time scale appropriate to the project
  Add each task and milestone

## Slide 5: Assigning Personnel
Convert the task effort to task duration
  In the simplest cases
  Divide the effort by the number of people assigned
If an individual is split between multiple tasks
  Do an allocation of that individual’s time across all tasks

## Slide 6: Assign a Start Time
Four possibilities
  Assign a fixed date / time
  Set start time to match the finish time for another task
  Set start time to match the finish time for another task plus a fixed delay
  Set the start time to produce a finish time to match the finish time for another task

## Slide 7: Draw a Time Scale
Linear scale
  Display project from beginning to end
  With convenient subdivisions

## Slide 8: Add Each Task and Milestone
Add tasks and milestones in order
  For tasks
    Draw a rectangle whose left edge aligns with the start time
    Length corresponds to the duration of the task
  For milestones
    Draw a diamond at the event time

## Slide 9: Schedule Example
Deliverables
  Design Document due 2 weeks after all designs are complete
  User Manual due at the end of integration
Milestones
  Design review 1 week prior to Design Document delivered
  System delivery 1 week after end of system testing

## Slide 10: Schedule Summary
To be useful, a schedule must be maintained
Review the schedule weekly
  Modifying the durations to correspond to over-runs and under-runs
  Compare the new schedule to the original schedule (baseline) to determine the effects of changes
Exceedingly laborious to manually prepare and maintain a Gantt chart
Use software tool to draw and maintain Gantt charts
  Microsoft Project

## Slide 11: Critical Path Analysis
A method of analyzing a complex schedule
CPA provides the project manager with
  The minimum time required to complete the project
  A means of prioritizing activities
    To achieve the scheduled completion date
  A rationale for reallocating resources
    To adjust for slippages in the schedule

## Slide 12: Critical Path Analysis (continued)
The underlying principle of CPA:
  Some activities in the project depend upon other activities
    The dependant activities must be completed in sequence
  Other activities may not depend upon the previous activities
    Have flexibility in scheduling these activities

## Slide 13: Critical Path How-To
Handout on Critical Path Analysis method

## Slide 14: Demonstration of CPA
Perform a CPA on the following project
Assume a 5 January start date

## Slide 15: Using the Network Diagram
Activities along the critical path are the ones that must be most closely monitored
  Any slippage in any of these tasks extends the finish date
If you want to compress the project
  Blindly throw a lot of resources at all tasks
  Apply resources just to tasks along the critical path
  Nota Bene
    Applying enough resources may define a “new” critical path

## Slide 16: PERT
Program Evaluation and Review Technique is a variation of Critical Path analysis
PERT takes a more conservative approach to estimating task durations
For each task, provide an estimate of
  The shortest likely time to complete a task - slt
  The most likely time to complete a task - mlt
  The longest likely time to complete a task – llt

## Slide 17: PERT (continued)
Calculate a task duration time as
The purpose of the 1, 4, 1 weighting is to give less importance to overly optimistic or pessimistic estimates

## Slide 18: Critical Path Analysis - Summary
CPA is an effective and powerful means of assessing
  What activities must be carried out
  Where parallel activity can be performed
  The shortest possible time to complete the project
  Resources needed to carry out the project
  Sequences and timing among the tasks
  Task priorities
  The most efficient way to allocate resources to compress the schedule