## Slide 1: Lecture 7 Risk Analysis
CSCI – 3350 Software Engineering II
Fall 2014
Bill Pine

## Slide 2: Introduction
Relation to Top 10 Risk List
Methodology for Quantifying
Setting Priority

## Slide 3: Setting Risk Priority
In a previous lecture, priority set by
  Expert opinion
  Intuition
  Whim
There are more rigorous techniques that may be employed
We will examine a few methods

## Slide 4: Rationale
All software project can benefit from risk analysis
Life and safety critical systems
  Subject to standards requiring rigorous risk analysis as an integral part of the development process
Other systems can also benefit

## Slide 5: Levels of Criticality
In The Methodology Space, Alistair Cockburn defines four levels of criticality
These can serve as a basis for risk mitigation
The levels are
  Loss of life
  Loss of essential money
  Loss of discretionary money
  Loss of comfort

## Slide 6: Levels of Criticality (cont)
The previous levels are in order of decreasing criticality
While risk analysis can be usefully applied to all levels
  The consequences of project failure, especially in the first two levels, mandates the use of risk analysis in software development

## Slide 7: Benefits To Non Critical Systems
Highlights potential problem areas
Provide developers with the tools to
  Identify the most important risks
  Rationally prioritize those risks
  Allocate resources to mitigate those risks
Techniques also of use to the software tester
  Select tests with, potentially, the highest payoff

## Slide 8: Components of Risk Analysis
Risk analysis is
  A well defined process
  Allows the engineer to set the priorities for the risk list
Consist of two components
  Assigning likelihood of occurrence to each risk
  Assessing the severity of the impact of the risk, should the issue occur

## Slide 9: Likelihood of Occurrence
Express as a probability
  Range 0 → 1.0
Fixed integer values
  Set of 3 values: 1, 2, 3
    Associate with levels: Low, Moderate, High
  Set of 5 values: 1, 2, 3, 4, 5
    Associate with levels: Very Low, Low, Moderate, High, Very High

## Slide 10: Likelihood of Occurrence (cont)
May be useful to provide a quantification
  For Example:
Level | Probability
Very Low | < 0.1
Low | ≥ 0.1 but < 0.4
Moderate | ≥ 0.4 but < 0.6
High | ≥ 0.6 but < 0.9
Very High | ≥ 0.9

## Slide 11: Severity of Impact
Fixed integer values
  Set of 4 values: 1, 2, 3, 4
  Associated with severities: Insignificant, Tolerable, Severe, Catastrophic

## Slide 12: Analysis Techniques
Two independent techniques
  Risk exposure
    Calculate the product of likelihood and impact
    Priority directly proportional to risk
  Risk matrix
    Scatter-plot of the likelihood / severity values
    Assign importance to severity or impact as appropriate
    Ignores the risk exposure value

## Slide 13: Example
Consider this project risk identification
ID | Description | Likelihood ( 1 – 10) | Severity (1-10) | Exposure
A | Key personnel leave | 1 | 10 | 10
B | Wrong requirements recorded | 2 | 1 | 2
C | Inappropriate user interface | 1 | 8 | 8
D | Un-needed features | 9 | 1 | 9
E | Uncontrolled customer changes | 6 | 7 | 42
F | Late delivery of graphics | 8 | 9 | 72
G | Poor user documentation | 5 | 3 | 15

## Slide 14: Threshold by Quadrant
P 1
P 2
P 3
P 4

## Slide 15: Alternate Threshold by Quadrant
P 1
P 2
P 3
P 4

## Slide 16: Threshold by Diagonals
P 1
P 2
P 3
P4

## Slide 17: High Severity Threshold
P 1
P 2
P 3
P 4
P 5

## Slide 18: Risk Matrix Types
Threshold by quadrant
  High severity more important than likelihood
Alternate threshold by quadrant
  High likelihood more important than severity
Threshold by diagonals
  Equal importance to likelihood and severity
High severity threshold
  Highest severity items on equal footing, then stress severity over likelihood

## Slide 19: Steps in Risk Analysis
Select a scale for likelihood and severity
Create a table, containing columns for risk name, likelihood and severity
Assign values for likelihood and severity to each risk
Select an analysis technique and apply it to the values assigned in step 3
Assign a priority to each risk based upon the results of step 4

## Slide 20: Summary
How fine a granularity for scales on severity and likelihood?
  Depends upon the situation
    Enough to separate the risks
    No so many as to make it hard to assign a value
Relative ranking more important than absolute value
Experienced person should assign the ranking

## Slide 21: Summary (cont)
Risk exposure doesn’t discriminate between high likelihood-low impact and low likelihood- high impact risks
Risk analysis provides a rational way of assigning risks